Should you require any information to help you with this Event Proposal, please refer to Club Management Training (CMT) Chapter 3 which covers “Event Preparation”.

| GENERAL Date: Select date |  |  |  |
| --- | --- | --- | --- |
| CLUB/COMMITTEE/ TEAM | Gamers’ Guild | CLUB MEMBERSHIP/ COHORT STRENGTH | 141 |
| REQUESTOR | Yan Chen |  |  |
| ACTIVITY/RAMS ID | Staff IC to enter | SLD STAFF IC | Keven |

| EVENT INFORMATION |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| TYPE OF EVENT | ☐ NEXUS ($6/pax, 1 mth lead time) |  | ☒ UNIFY ($10/pax, 3 mth lead time) |  | ☐OTHERS |
|  | Please explain if date of application is less than required lead time: Planning was pushed due to club fair and other subsequent events |  |  |  |  |
| EVENT NAME | Club Clash |  |  |  |  |
| EVENT OBJECTIVES | Describe the desired outcomes (observable behaviours, output and/or statistics) that the event aims to achieve. |  |  |  |  |
| PART OF ANNUAL WORK PLAN? | ☒ Yes ☐ No, please explain: Enter text |  |  |  |  |
| EVENT DETAILS | Date: Select date | Time: e.g. 1300 – 1630 hrs |  | Venue: Enter text |  |
|  | Target: 65 pax (incl. Organising Committee, and student helpers) | To tally with SL-GOV-FM-005A Event Budget |  |  |  |
|  |  | Event Expenditure: $Enter Cost (excl. GST) |  | Event Funding & Collection: $Enter Cost (excl. GST) |  |
|  | Please explain if you wish to request for additional budget beyond SLD allowable funding guideline (subject to approval). |  |  |  |  |

ADDITIONAL EVENT INFORMATION (if applicable)

| EXTERNAL BENEFICIARIES | ☐ Yes, list no. of person(s) to be impacted: Enter text ☐ No List beneficiary organisation. |
| --- | --- |
| EVENT SUPPORTER(S) | Enter name of individual(s) and/or external organisation(s) and corresponding type of support (e.g. advisory, venue, etc.) provided, if applicable. |
| DANGEROUS EQUIPMENT (Check if applicable) | ☐ Entertainment laser ☐ Fireworks/ pyrotechnics ☐ Open flame cooking ☐ LPG cylinders ☐ Others, please specify: Enter text |

| TARGET NO. OF PARTICIPANTS |  |  |
| --- | --- | --- |
| PARTICIPANTS | NO. PAX | % |
| Students | 56 | % |
| Student Organisers - Gwendolyn - Pei Sheng - Manav - Clement - Tammy - Yan Chen - Esmund | 7 | % |
| Event Helper (if any) - Dennis - Ryan | 2 additional Helpers outside of EXCO | % |
| TOTAL | 65 | 100 % |

| ORGANISING COMMITTEE |  |  |  |
| --- | --- | --- | --- |
| NO | NAME | STUDENT ID | POSITION |
|  | Enter text | Enter text | Pls select |
|  | Enter text | Enter text | Pls select |
|  | Enter text | Enter text | Pls select |
|  | Enter text | Enter text | Pls select |

| PROGRAMME/ TRAINING SCHEDULE |  |  |  |
| --- | --- | --- | --- |
| DATE/ TIME | AGENDA (Programme Line-up) | PIC/ SPEAKER/ INSTRUCTOR | DETAILED DESCRIPTION (Activity steps, instructions, tasks, topics, etc.) |
| 7/12/24 11am-1130am | Week 1 game: League of Legends (ARAM) – Check in | Enter name | Starting time: 11am, games official start at 1130am Estimated 1 game: 25mins, Worst case scenario: 30mins 7 batches of 4 Games running simultaneously Breaks 5min between each game |
| 7/12/24 12pm | Match 1 |  |  |
| 7/12/24 12.30pm | Match 2 |  |  |
| 7/12/24 1pm | Match 3 |  |  |
| 7/12/24 1.30pm | Match 4 |  |  |
| 7/12/24 2pm | Match 5 |  |  |
| 7/12/24 2.30pm | Match 6 |  |  |
| 7/12/24 3pm | Match 7 |  |  |
| 14/12/24 11am-1130am | Week 2 game: Apex Legends (Hide & Seek) – Check in Seekers would be from EXCO |  | Starting time: 11am, games official start at 1130am 3 games: Estimated 2hrs Breaks 5min between each game |
| 14/12/24 12pm | Match 1 |  |  |
| 14/12/24 12.40pm | Match 2 |  |  |
| 14/12/24 1.20pm | Match 3 |  |  |
| 21/12/24 11am-1130am | Week 3 game: Stumble Guys – Check in |  | Starting time: 11am, games official start at 1130am 3 games: Estimated 2hrs Breaks 5min between each game |
| 21/12/24 12pm | Match 1 |  |  |
| 21/12/24 12.45pm | Match 2 |  |  |
| 21/12/24 1.15pm | Match 3 |  |  |
| 28/12/24 11am-1130am | Week 4 game: Valorant (SwiftPlay) – Check in |  | Starting time: 11am, games official start at 1130am Estimated 1 game: 15mins 7 batches of 4 Games running simultaneously Breaks 5min between each game |
| 28/12/24 12pm | Match 1 |  |  |
| 28/12/24 12.30pm | Match 2 |  |  |
| 28/12/24 1pm | Match 3 |  |  |
| 28/12/24 1.30pm | Match 4 |  |  |
| 28/12/24 2pm | Match 5 |  |  |
| 28/12/24 2.30pm | Match 6 |  |  |
| 28/12/24 3pm | Match 7 |  |  |
| 29/12/24 | Award ceremony + Party (pre-year end celebration?) |  | Starting time: 11am |

Event Layout (if applicable) Valorant & LoL Bracketing System (Round Robin): Apex Legends (Hide and Seek) Rules:

4 Games: League of Legends Valorant (SwiftPlay) Stumble Guys Apex Legends (Hide and Seek)

CONTINGENCY PLAN (if applicable)

e.g. wet weather/ haze/ speaker unavailable/ low registration Online Event

ADDITIONAL INFORMATION (if applicable)

The Organising Committee to list down any additional information required of participants for Staff IC to input in IN4SIT. Examples: - Dietary restrictions – Vegetarian, Others - Shirt Sizes – S, M, L, XL, XXL The Organising Committee may wish to approach the following clubs for their assistance for the event: - SIT Photographer Club – Event photography - SIT Civil Defence LionHearters Club – First aiders Enter text

| EVENT PLANNING TIMELINE |  |  |
| --- | --- | --- |
| DATE | DESCRIPTION | ACTION BY |
| 16/9/24 | Submit Event Proposal | Esmund |
| 20/9/24 | Receive approval on Event Proposal | Esmund |
| 20th – 23rd Sept 2024 | Blast of interest check/ outreach to all clubs Gwendolyn - Sports Pei Sheng – Student Chapters Manav – Performing Arts Tammy – Special Interest, SMCs Have a Excel document of collated clubs and checklist to tick off those we have contacted | PIC |
| DD/MM/YYYY | Enter text | PIC |

| EVENT LOGISTICS |  |  |  |  |
| --- | --- | --- | --- | --- |
| S/N | ITEMS | QTY | SOURCE | REMARKS/ POTENTIAL VENDOR |
|  | Enter text | Qty | Pls select | Enter text |
|  | Enter text | Qty | Pls select | Enter text |
|  | Enter text | Qty | Pls select | Enter text |

| DOCUMENTS TO SUBMIT |  |  |
| --- | --- | --- |
| S/N | DESCRIPTION | CHECK |
| COMPULSORY |  |  |
|  | SL-GOV-FM-005A Event Budget Template | ☐ |
|  | Risk Assessment and Management (RAMS) Form For online activities, please refer to “SLD-led & Student-led Online Activities” for approved risk controls. For a list of standard RAMs, you may refer to the Student Resources Page. | ☐ |
|  | SL-GOV-FM-011 Emergency Management Plan If your event is taking place at a specific campus, you may attach an EMP that is for a specific campus. Other templates are available on the Student Resources Page. | ☐ |
|  | Event Publicity Tag @SIT.studentlife or hashtag #SITStudentLife on Club/Committee’s IG postings, stories or captions for SL’s supported initiatives, activities, training, etc. | ☐ |
| If applicable/ Optional |  |  |
|  | If applicable, to be submitted at least 2 months prior (for Unify) / 3 weeks prior (for Nexus) to Event Date: |  |
|  | - EDM (jpeg) To submit two formats in landscape and square. | ☐ |
|  | - T-Shirt Design (jpeg) | ☐ |
|  | - E.g. Quotation – Vendor A [purpose] | ☐ ☐ |
|  | Request Form for External Guest, Speaker and Trainer. - To be submitted for approval together with the Event Proposal. - Only approach External Guest, Speaker and Trainer after approval is sought. | ☐ |
|  | If applicable, you can access other forms available on the Student Resources Page. |  |
| SUBMITTED BY: Enter name. Enter designation. |

| FOR OFFICIAL USE: |  |
| --- | --- |
| Approved Budget: No of Pax: No. pax Cost Per Pax: $Enter Cost SLD Funding: $Enter Cost |  |
| Comments: Enter text |  |
| APPROVED BY: (Staff IC/Team Lead) Date: Select date | Enter name. Enter designation. |
| Applicable only if Event is not listed in Work Plan OR Event Budget exceeds SLD Funding Guidelines OR Projected Total Event Expenditure exceeds $5,000: |  |
| APPROVED BY: (DD/HOD) Date: Select date | Enter name. Enter designation. |

Venue: Organising Committee to book SIT facilities through the Resource Booking System (RBS) or the Staff IC.

Complete SL-GOV-FM-005A Event Budget to fill in this portion.

A person or group outside of SIT that will benefit from this event.

Individual(s) within or outside of SIT and/or organisation(s) that are supporting this event by providing advisory input.

Maximum 6 persons or 10% of total number of participants for the event, whichever is lower.

Please note lead time required for items, e.g. shirt printing, food ordering etc. in overall timeline.

Students to check with Staff IC if items can be provided by SLD or by the Club/SMC or need to be purchased.